## Hoja 1
Pull Request |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9
Gantt Diagram |  | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V | L | M | M | J | V
Project SetUp | bar: Week 1 L to Week 1 M
Configure Flutter Dev Env | 1d | bar: Week 1 L
Oauth Application Registration | 1d | bar: Week 1 M
Source Control Repository SetUp | 1d | bar: Week 1 M
APP | bar: Week 1 L to Week 8 J
UX Design | 1w | bar: Week 1 L to Week 1 V
Home Screen | 1d | bar: Week 2 L
Playlist Selection Screen | 1d | bar: Week 2 M
Playlist Details Screen | 1d | bar: Week 2 M
Playlist Transfer Screen | 1d | bar: Week 2 J
Transfer History Screen | 1d | bar: Week 2 V
Spotify Autentication | 1w | bar: Week 3 L to Week 3 V
YTM Autentication | 1w | bar: Week 4 L to Week 4 V
Backend Integration | 3d | bar: Week 7 L to Week 7 M
Transfer status SSE UX integration | 2d | bar: Week 7 V to Week 8 L
Transfer Summary Screen | 3d | bar: Week 8 M to Week 8 J
Backend | bar: Week 3 L to Week 7 V
API Endpoint Design | 1w | bar: Week 3 L to Week 3 V
Library to translate song ID's YTM <-> Spotify | 1w | bar: Week 4 L to Week 4 V
Endpoint to receive and store auth tokens | 3d | bar: Week 5 L to Week 5 M
Endpoint to list all user's playlists | 3d | bar: Week 5 J to Week 6 L
Endpoint to transfer a playlist | 4d | bar: Week 6 M to Week 6 V
Transfer status SSE | 4d | bar: Week 7 L to Week 7 J
Exponential Backoff / Retry Logic | 1d | bar: Week 7 V
QA | bar: Week 7 J to Week 9 J
Song translation Unit Testing | 3d | bar: Week 7 J to Week 8 L
API Endpoint Unit Testing | 3d | bar: Week 8 M to Week 8 J
End to End manual testing (500+ songs) | 1d | bar: Week 9 J
Deployment | bar: Week 8 V to Week 9 M
Move backend to a dedicated VPS | 4d | bar: Week 8 V to Week 9 M
Critical Path | 44 d