## Resumen Total
PullRequest - Resumen de Costo Total
Proyecto universitario ¦ 3 ingenieros junior ¦ Tarifa: $150 MXN/h
Equipo de Desarrollo
Integrante | Rol | Horas | Costo MXN
Ingeniero 1 | Frontend / UX | 136 | 20400
Ingeniero 2 | Backend | 200 | 30000
Ingeniero 3 | Auth / QA / DevOps | 200 | 30000
Total Equipo |  | 536 | 80400
Costo por Area de Trabajo
Area | Horas | Costo MXN | Costo USD
Project SetUp | 24 | 3600 | 180
APP (Frontend Flutter) | 224 | 33600 | 1680
Backend | 200 | 30000 | 1500
QA | 56 | 8400 | 420
Deployment | 32 | 4800 | 240
Total | 536 | 80400 | 4020
Infraestructura (6 meses - duracion del curso)
Concepto | Minimo | Maximo
VPS Backend (6 meses) | $60 USD | $150 USD
APIs terceros | $0 | $0
Tiendas de apps (opcional) | $0 | $124 USD
Dominio + SSL | $0 | $15 USD
Total Infraestructura | $60 USD (~$1,200 MXN) | $289 USD (~$5,780 MXN)
COSTO TOTAL DEL PROYECTO
Concepto | Costo MXN | Costo USD
Desarrollo (536h) | $80,400 | ~$4,020
Infraestructura (min) | ~$1,200 | $60
Infraestructura (max) | ~$5,780 | $289
TOTAL MINIMO | $81,600 MXN | ~$4,080 USD
TOTAL MAXIMO | $86,180 MXN | ~$4,309 USD
Buffer de Contingencia (15-20%)
Escenario | Adicional MXN | Adicional USD
Con 15% contingencia | +$12,060 | +$603
Con 20% contingencia | +$16,080 | +$804

## Desglose por Actividad
PullRequest - Desglose de Costos por Actividad
Ruta Critica: 44 dias ¦ 9 semanas ¦ 3 ingenieros junior ¦ $150 MXN/h
Actividad | Duracion | Horas | Costo MXN | Responsable
PROJECT SETUP
Configure Flutter Dev Env | 1d | 8 | 1200 | Ing. 1
OAuth Application Registration | 1d | 8 | 1200 | Ing. 3
Source Control Repository SetUp | 1d | 8 | 1200 | Ing. 1
Subtotal Project SetUp | 3d | 24 | 3600
APP (FRONTEND FLUTTER)
UX Design | 1w (5d) | 40 | 6000 | Ing. 1
Home Screen | 1d | 8 | 1200 | Ing. 1
Playlist Selection Screen | 1d | 8 | 1200 | Ing. 1
Playlist Details Screen | 1d | 8 | 1200 | Ing. 1
Playlist Transfer Screen | 1d | 8 | 1200 | Ing. 1
Transfer History Screen | 1d | 8 | 1200 | Ing. 1
Spotify Authentication | 1w (5d) | 40 | 6000 | Ing. 3
YTM Authentication | 1w (5d) | 40 | 6000 | Ing. 3
Backend Integration | 3d | 24 | 3600 | Ing. 3
Transfer status SSE UX integration | 2d | 16 | 2400 | Ing. 1
Transfer Summary Screen | 3d | 24 | 3600 | Ing. 1
Subtotal APP | 28d | 224 | 33600
BACKEND
API Endpoint Design | 1w (5d) | 40 | 6000 | Ing. 2
Library to translate song IDs YTM <-> Spotify | 1w (5d) | 40 | 6000 | Ing. 2
Endpoint to receive and store auth tokens | 3d | 24 | 3600 | Ing. 2
Endpoint to list all user playlists | 3d | 24 | 3600 | Ing. 2
Endpoint to transfer a playlist | 4d | 32 | 4800 | Ing. 2
Transfer status SSE | 4d | 32 | 4800 | Ing. 2
Exponential Backoff / Retry Logic | 1d | 8 | 1200 | Ing. 2
Subtotal Backend | 25d | 200 | 30000
QA
Song translation Unit Testing | 3d | 24 | 3600 | Ing. 3
API Endpoint Unit Testing | 3d | 24 | 3600 | Ing. 3
End to End manual testing (500+ songs) | 1d | 8 | 1200 | Ing. 3
Subtotal QA | 7d | 56 | 8400
DEPLOYMENT
Move backend to a dedicated VPS | 4d | 32 | 4800 | Ing. 3
Subtotal Deployment | 4d | 32 | 4800
TOTAL PROYECTO | 67d | 536 | 80400
Tarifa unica: $150 MXN/hora (Ingeniero Junior)
Leyenda de colores:
Ing. 1 - Frontend/UX
Ing. 2 - Backend
Ing. 3 - Auth/QA/DevOps

## Costo por Ingeniero
PullRequest - Detalle de Costo por Ingeniero
Ingeniero 1 - Frontend / UX (136 h)
Actividad | Horas | Costo MXN | Costo USD
Configure Flutter Dev Env | 8 | 1200 | 60
Source Control Repository SetUp | 8 | 1200 | 60
UX Design | 40 | 6000 | 300
Home Screen | 8 | 1200 | 60
Playlist Selection Screen | 8 | 1200 | 60
Playlist Details Screen | 8 | 1200 | 60
Playlist Transfer Screen | 8 | 1200 | 60
Transfer History Screen | 8 | 1200 | 60
Transfer status SSE UX integration | 16 | 2400 | 120
Transfer Summary Screen | 24 | 3600 | 180
Subtotal | 136 | 20400 | 1020
Ingeniero 2 - Backend (200 h)
Actividad | Horas | Costo MXN | Costo USD
API Endpoint Design | 40 | 6000 | 300
Library to translate song IDs YTM <-> Spotify | 40 | 6000 | 300
Endpoint to receive and store auth tokens | 24 | 3600 | 180
Endpoint to list all user playlists | 24 | 3600 | 180
Endpoint to transfer a playlist | 32 | 4800 | 240
Transfer status SSE | 32 | 4800 | 240
Exponential Backoff / Retry Logic | 8 | 1200 | 60
Subtotal | 200 | 30000 | 1500
Ingeniero 3 - Auth / QA / DevOps (200 h)
Actividad | Horas | Costo MXN | Costo USD
OAuth Application Registration | 8 | 1200 | 60
Spotify Authentication | 40 | 6000 | 300
YTM Authentication | 40 | 6000 | 300
Backend Integration | 24 | 3600 | 180
Song translation Unit Testing | 24 | 3600 | 180
API Endpoint Unit Testing | 24 | 3600 | 180
End to End manual testing (500+ songs) | 8 | 1200 | 60
Move backend to a dedicated VPS | 32 | 4800 | 240
Subtotal | 200 | 30000 | 1500
TOTAL PROYECTO (3 Ingenieros) | 536 | 80400 | 4020

## Infraestructura
PullRequest - Costos de Infraestructura
Periodo estimado: 6 meses (duracion del curso universitario)
APIs y Plataformas
Servicio | Costo/mes | Costo 6 meses | Notas
Spotify Web API | $0 | $0 | Gratuita (rate limits)
YouTube Data API v3 | $0 | $0 | Capa gratuita suficiente para uso academico
Google Cloud (OAuth) | $0 | $0 | Capa gratuita
VPS Dedicado (Backend)
Proveedor | Costo/mes | Costo 6 meses | Specs
DigitalOcean/Hetzner/Linode | $10-$25 USD | $60-$150 USD | 2vCPU, 4GB RAM, 80GB
Railway/Render | $5-$20 USD | $30-$120 USD | Serverless/managed
Tiendas de Aplicaciones (opcional)
Concepto | Costo | Frecuencia | Notas
Google Play Developer | $25 USD | Unico | Solo si se publica en Play Store
Apple Developer Program | $99 USD | Anual | Solo si se publica en App Store
TOTAL INFRAESTRUCTURA (6 meses) | Min: $60 USD | Max: $289 USD
Equivalente MXN | ~$1,200 MXN | ~$5,780 MXN

## Mantenimiento
PullRequest - Mantenimiento Post-Lanzamiento
Aplicable si el proyecto continua despues de la entrega academica
Actividad | Horas/mes | Costo/mes MXN | Costo/mes USD | Costo/ano USD
Correccion de bugs (app+backend) | 10 | 1500 | 75 | 900
Actualizaciones dependencias Flutter | 4 | 600 | 30 | 360
Mantenimiento backend y VPS | 6 | 900 | 45 | 540
Cambios en APIs Spotify/YouTube | 6 | 900 | 45 | 540
Actualizacion libreria traduccion IDs | 4 | 600 | 30 | 360
Nuevas features menores | 8 | 1200 | 60 | 720
TOTAL MANTENIMIENTO | 38 | 5700 | 285 | 3420